## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project setup and Streamlit environment | MUST HAVE | No Dependency | Deepak Kumar | 3-Completed
S1 | S1 | US-002 | Workflow creation and project documentation | MUST HAVE | No Dependency | Deepak Kumar | 3-Completed
S2 | S2 | US-003 | Integrate Shodan API for vulnerability scanning | MUST HAVE | Shodan API | Deepak Kumar | 3-Completed
S2 | S2 | US-004 | Fetch IP data and analyze open ports | SHOULD HAVE | Internet | Deepak Kumar | 3-Completed
S3 | S3 | US-005 | Implement risk scoring system | MUST HAVE | Python Logic | Deepak Kumar | 3-Completed
S4 | S4 | US-006 | Build Streamlit dashboard UI | MUST HAVE | Streamlit | Deepak Kumar | 3-Completed
S5 | S5 | US-007 | Display vulnerabilities and risk levels | MUST HAVE | Data Processing | Deepak Kumar | 3-Completed
S6 | S6 | US-008 | Testing and debugging | SHOULD HAVE | Testing Tools | Deepak Kumar | 2-In Progress
S7 | S7 | US-009 | Integration and optimization | SHOULD HAVE | System Integration | Deepak Kumar | 2-In Progress
S8 | S8 | US-010 | Deployment and final submission | MUST HAVE | GitHub | Deepak Kumar | 2-In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day
[8 empty] | 76 | 4.5 | 5 |  | 4.5 | 5 | 7 | 3.5 | 4 | 5.5 | 3.5 | 7.5 | 7.5 | 3.5 | 5
SPRINT 1 BACKLOG
US-001 | 1 | Project setup and environment configuration | 2026-02-20 | 2026-02-22 | Deepak Kumar | Setup | 3-Completed | 4 | 0 | 1 | 1 | 0 | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | Project documentation and workflow design | 2026-02-23 | 2026-02-25 | Deepak Kumar | Design | 3-Completed | 5 | 0 | 0 | 1.5 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0.5 |  | 0
US-003 | 3 | Shodan API integration | 2026-02-26 | 2026-03-02 | Deepak Kumar | Coding | 3-Completed | 10 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 2 | 1 | 1 | 1
US-004 | 4 | IP data fetching and processing | 2026-03-03 | 2026-03-06 | Deepak Kumar | Coding | 3-Completed | 8 | 0.5 | 1 | 1 | 0.5 | 1 | 1 | 0 | 0 | 1 | 0 | 0.5 | 0 | 0.5 | 1
US-005 | 1900-01-04 | Risk scoring implementation | 2026-03-07 | 2026-03-11 | Deepak Kumar | Coding | 3-Completed | 10 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0.5 | 1 | 1 | 0.5 | 2 | 0 | 1
US-006 | 1900-01-05 | Streamlit dashboard development | 2026-03-12 | 2026-03-16 | Deepak Kumar | UI Development | 3-Completed | 14 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0.5 | 1.5
US-007 | 1900-01-06 | Display results and visualization | 2026-03-17 | 2026-03-19 | Deepak Kumar | Build | 3-Completed | 6 | 1 | 0 | 1 | 0.5 | 0.5 | 0 | 0 | 0.5 | 1 | 0 | 1 | 0 | 0.5 | 0
US-008 | 1900-01-07 | Testing and debugging | 2026-03-20 | 2026-03-22 | Deepak Kumar | Testing | 2-In Progress | 8 | 0 | 1 | 1 | 0.5 | 0 | 0.5 | 0.5 | 0 | 1 | 0 | 1 | 1 | 1 | 0.5
US-009 | 1900-01-08 | System integration | 2026-03-23 | 2026-03-24 | Deepak Kumar | Integration | 2-In Progress | 6 | 0.5 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 0 | 1 | 1 | 1 | 0 | 0
US-010 | 1900-01-09 | Deployment and GitHub upload | 2026-03-25 | 2026-03-26 | Deepak Kumar | Deployment | 2-In Progress | 5 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 4 | Difficulty integrating Shodan API | Studied API documentation and implemented proper requests
Sprint 2 | Day 8 | Error in risk score calculation | Debugged logic and tested with sample inputs
Sprint 3 | Day 12 | UI not displaying correctly | Fixed layout issues in Streamlit
Sprint 4 | Day 16 | Data not updating properly | Improved data handling logic
Sprint 5 | Day 20 | Bugs during testing | Fixed errors and optimized performance
Sprint 6 | Day 23 | Integration issues between modules | Refactored code and tested modules separately

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-20 | 2026-02-24 | Deepak Kumar | Planning project structure | Ignoring proper design | Learning project modules | Created proper folder structure
2 | Sprint 2 | 2026-02-25 | 2026-03-01 | Deepak Kumar | Using APIs effectively | Hardcoding sensitive data | Testing API results | Integrated Shodan API successfully
3 | Sprint 3 | 2026-03-02 | 2026-03-08 | Deepak Kumar | Improving logic building | Using static values | Optimizing calculations | Implemented risk scoring system
4 | Sprint 4 | 2026-03-09 | 2026-03-15 | Deepak Kumar | Designing UI | Poor visualization | Improve UI design | Built Streamlit dashboard
5 | Sprint 5 | 2026-03-16 | 2026-03-20 | Deepak Kumar | Debugging and testing | Ignoring edge cases | Fixing errors | Improved system performance
6 | Sprint 6 | 2026-03-21 | 2026-03-26 | Deepak Kumar | Final deployment | Skipping documentation | Maintaining code quality | Uploaded project on GitHub